## Extreme Networks-Build Analysis
User Story# | Entity | Scenario Description | Failed step | Comment | Role
US-004227 | Cases | Entitlements-Milestones | And I verify the Case "Milestone Name" details | Unable to see the Case Milestone information | Admin and APAC Sales Ops
US-004227 | Cases | Quote Request - Entitlements-Milestones - Reporting Request - Entitlements-Milestones Lead Submission - Entitlements-Milestones | 1.And I select the "Priority" is "Low" 2.And I select the "Priority" is "High" 3.And I verify the Case "Milestone Name" details | Unable to see the Case Milestone information for "Priority" is "Low" and "Priority" is "High" | APAC Ops Manager, APAC Ops Rep, APAC Sales Manager, APAC Sales Rep, EMEA Ops Manager, EMEA Ops Rep, EMEA Sales Manager, EMEA Sales Rep, EMEA Sales Ops, NALA Ops Manager, NALA Ops Rep, NALA Sales Manager, NALA Sales Rep and NALA Sales Ops
US-004227 | Cases | Booking Request - Entitlements-Milestones | 1.And I select the "Priority" is "Normal" 2.And I verify the Case "Milestone Name" details | Getting wrong case Time Remaining | APAC Ops Manager, APAC Ops Rep, APAC Sales Manager, APAC Sales Rep
US-004233 | Cases | "Renewal Status" pickList | Then I verify the House Account "Renewal Status" pickList values | Unable to see the "Renewal Status" pickList | Sales Manager and Sales Rep
US-004234 | Cases | Booking Request | Then I verify the "Booking Request" case status "Ready" updated successfully | Failed to updated the status value "Ready" in case details page | Ops Manager and Ops Rep
US-004235 | General | Turn on TRACKINGS | I should see Track History checkbox check for "ServiceSource1__REN_Expiration_Quarter_Year__c" | FAIL - Track History for the field -ServiceSource1__REN_Expiration_Quarter_Year__c - is NOT checked | Admin
US-004235 | General | Turn on TRACKINGS | I should see Track History checkbox check for "SyncedQuoteId" | FAIL - Track History for the field -SyncedQuoteId - is NOT checked | Admin
US-004237 | Quotes | Update Quote and Quote Picklist | I should see the field "Local Currency Code" is present under "Renewal Relationship" section | The section - Renewal Relationship - is not present over the page | All Role
US-004237 | Quotes | Update Quote and Quote Picklist | I should see "Local Currency Code" field picklist options | The following values should be visible: TBD | All Role
US-004225 | Multi Currency | Setup Multi-Currency -Opportunity- Local Renewal Target | I should see some value in "Local Renewal Target" field | The field "Local Renewal Target" is not sowing any data. (Opportunity record used to test the scenario is - "smoke-test-mc-avi") | Ops Mggr, Sales Mgr