## Overview
Use Case Scenario | Test Case Name | Test Script Status | Owner | # of Test Steps | Passed | Failed | Not Tested
General |  |  |  | 18 | 17 | 0 | 1
US-003686 | Base Configuration | Complete | Mailene | 5
US-003688 | Added Tokyo timezone to Business Hours tab | Complete | Mailene | 5
US-003690 | Disabled Rule: SSI_ZTH__Stage_Closed_Sale | Complete | Mailene | 5
US-003692 | Updated Users tab to align users | Complete | Mailene | 3
Accounts |  |  |  | 0 | 0 | 0 | 0
No User Story# | Tab is hidden |  |  | 0
Contacts |  |  |  | 0 | 0 | 0 | 0
No User Story# | Tab is hidden |  |  | 0
Opportunities |  |  |  | 19 | 9 | 2 | 8
US-003694 | Add Google SFDC ID, Original Order Number & Direct/Channel to page layout | Completed | Mailene | 5
US-003695 | Add Picklist for Client Region, Client Theatre, Currency, Engagement type and Client Territory | Completed | Mailene | 5
US-003696 | Update Opportunity Product | Completed | Mailene | 5
US-003697 | Update to Renewable Line Item | Completed | Mailene | 4
US-003690 | Disabled Rule: SSI_ZTH__Stage_Closed_Sale | Completed | Mailene | 4
Cases |  |  |  | 45 | 27 | 4 | 14
US-003693 | Case Types by Persona | Completed | Mailene | 20
US-003687 | Changed Custom to 'Yes' for all SLA's | Completed | Mailene | 11
US-003689 | Disable No Service Approval process. | Completed | Mailene | 14
US-003691 | Disable all requirements for approval for No Services only | Incomplete | Mailene | 0
Tasks |  |  |  | 12 | 0 | 0 | 12
US-003698 | Task Types by Persona | Completed | Mailene | 12
Leads |  |  |  | 0 | 0 | 0 | 0
No User Story# | Tab is hidden | Incomplete | Mailene | 0
Total |  |  |  | 94 | 53 | 6 | 35

## General
Use Cases # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003686 | Base Configuration - Currency, | Configuration | Admin | Navigate to "Home" tab |  | Home tab load |  | Passed |  |  | Passed | 17
US-003686 |  |  |  | Click on username in the top right corner then select "Setup" |  | Force.com Home page load |  | Passed |  |  | Failed | 0 | Passed
US-003686 |  |  |  | From Administration Setup, expand "Company Profile" |  | Company Profile expand |  | Passed |  |  |  |  | Failed
US-003686 |  |  |  | Click on "Manage Currencies" |  | Active Currencies table load |  | Passed |  |  |  |  | Not Tested
US-003686 |  |  |  | Verify Currency setting |  | Currency should shows: JPY USD GBP EUR |  | Passed |  | How to verify Currency by Geo
US-003688 | Added Tokyo timezone to Business Hours tab |  |  | Click on "Business Hours" |  | Organization Business Hours page load |  | Passed
US-003688 |  |  |  | Click on "APAC (TOK)" |  | APAC (TOK): Sunday: No Hours Monday: 8:00 AM to 12:00 AM Tuesday 24 Hours Wednesday 24 Hours Thursday 24 Hours Friday 12:00 AM to 5:00 PM Saturday No Hours |  | Passed
US-003688 |  |  |  | Click on "APAC (SIN/KL)" |  | APAC (SIN/KL): Sunday: No Hours Monday: 8:00 AM to 12:00 AM Tuesday 24 Hours Wednesday 24 Hours Thursday 24 Hours Friday 12:00 AM to 5:00 PM Saturday No Hours |  | Passed
US-003688 |  |  |  | Click on NALA |  | NALA: Sunday: No Hours Monday: 8:00 AM to 12:00 AM Tuesday 24 Hours Wednesday 24 Hours Thursday 24 Hours Friday 12:00 AM to 5:00 PM Saturday No Hours |  | Passed
US-003688 |  |  |  | Click on EMEA |  | EMEA: Sunday: No Hours Monday: 8:00 AM to 12:00 AM Tuesday 24 Hours Wednesday 24 Hours Thursday 24 Hours Friday 12:00 AM to 5:00 PM Saturday No Hours |  | Passed
US-003690 | Disabled Rule: SSI_ZTH__Stage_Closed_Sale |  |  | Click on "App Setup" arrow |  | App Setup list expand |  | Passed
US-003690 |  |  |  | Click on "Customize" arrow |  | Customize list expand |  | Passed
US-003690 |  |  |  | Click on "Opportunities" arrow |  | Opportunities list expand |  | Passed
US-003690 |  |  |  | Click on "Validation Rules" |  | Opportunity Validation Rules page load |  | Passed
US-003690 |  |  |  | Verify "Stage_Closed_Sale" rule setting |  | Stage_Closed_Sale active checkbox should be unchecked |  | Passed
US-003692 | Updated Users tab to align users |  |  | From Administration Setup, click on "Manage Users" arrow |  | Manage Users list expand |  | Passed
US-003692 |  |  |  | Click on "Users" |  | All Users table load |  | Passed
US-003692 |  |  |  | Verify list of user |  | All users from "Users" tab should be available and have the correct: Username First & Last Name Status Persona |  | Not Tested
Passed
Failed
Note on A44: Mailene Mac: Need to add scripts for Batch Jobs

## Accounts (hidden)
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
[11 empty] | Passed | 0
[11 empty] | Failed | 0 | Passed
Failed
Not Tested
Not Tested

## Contacts (hidden)
Passed | 0
Failed | 0 | Passed
Failed
Not Tested

## Users
Update |  | User Register (Add lines for deployed Users)
User Story | Custom | Username | LastName | FirstName | User Status | Persona | Profile | Public Group | GridBuddy | Data.com | Channel | Channel Community | Channel Community | Channel NetOps | CLM Quote Extension | CSM | CSM NetOps | Entitlements Extension | Lookup Rollup Summaries - Configure Rollups | Lookup Rollup Summaries - Process Rollups | NonCSM | Renew | Renew NetOps | SSI Zenith Admin Permission | SSI Zenith Data Services Permission | SSI Zenith Manage Public List View Permission | SSI Zenith Manage Report & Dashboard Permission | SSI Zenith Operation Services Manager Permission | SSI Zenith Operation Services Rep Permission | SSI Zenith Read Only Permission | SSI Zenith Sales Manager Permission | SSI Zenith Sales Rep Permission | Usage Event Log Access (use only for API users)
US-003692 | Yes | ajackson@servicesource.com | Jackson | Adam | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | apancake@servicesource.com | Pancake | Alexis | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | avelasco@servicesource.com | Velasco | Ana | Active | Operations Rep | SSI Zenith Operations Services | Sales Ops Users |  |  | x |  |  |  | x | [6 empty] | x | [6 empty] | x
US-003692 | Yes | avrignon@servicesource.com | Vrignon | Anatole | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | amanus@servicesource.com | Manus | Andrew | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | annrogers@servicesource.com | Rogers | Anna | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | aspindler@servicesource.com | Spindler | Anna | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | adeal@servicesource.com | Deal | Ashley | Active | Sales Manager | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x |  |  |  |  | x |  |  |  | x
US-003692 | Yes | aarchila@servicesource.com | Archila | Ana | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | bmatthews@servicesource.com | Matthews | Broc | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | cquek@servicesource.com | Quek | Cat | Active | Sales Operations Analyst | SSI Zenith Read Only | Sales Ops Users |  |  | x | [15 empty] | x |  |  | x
US-003692 | Yes | chudson@servicesource.com | Hudson | Catherine | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | chardage@servicesource.com | Hardage | Charles | Active | Sales Manager | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x |  |  |  |  | x |  |  |  | x
US-003692 | Yes | croman@servicesource.com | Roman | Chyna | Active | Sales Manager | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x |  |  |  |  | x |  |  |  | x
US-003692 | Yes | cpascoal@servicesource.com | Pascoal | Christina | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | dadavies@servicesource.com | Davies | David | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | emarquina@servicesource.com | Marquina | Enrique | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | fzucchini@servicesource.com | Zucchini | Fabien | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | fmcgrath@servicesource.com | McGrath | Fiach | Active | Sales Manager | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x |  |  |  |  | x |  |  |  | x
US-003692 | Yes | gvillanueva@servicesource.com | Villanueva - Chung | Gemma Katrina | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | jdarretta@servicesource.com | Darretta | Josh | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | jmorel@servicesource.com | Morel | Julien | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | kviduto@servicesource.com | Viduto | Katazyna | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | khasan@servicesource.com | Hasan | Kawees | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | kchau@servicesource.com | Chau | Khanh | Active | Operations Rep | SSI Zenith Operations Services | Sales Ops Users |  |  | x |  |  |  | x | [6 empty] | x | [6 empty] | x
US-003692 | Yes | lschofield@servicesource.com | Schofield | Leah | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | lcefali@servicesource.com | Cefali | Luca | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | lhayaux@servicesource.com | Hayaux | Lucas | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | lblanco@servicesource.com | Blanco | Luna | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | mmassey@servicesource.com | Massey | Madeline | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | mvedjelova@servicesource.com | Iring | Maria | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | mbagby@servicesource.com | Bagby | Matt | Active | Sales Operations Analyst | SSI Zenith Read Only | Sales Ops Users |  |  | x | [15 empty] | x |  |  | x
US-003692 | Yes | mguagnino@servicesource.com | Guagnino | Mattia | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | mlem@servicesource.com | Lem | Max | Active | Sales Manager | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x |  |  |  |  | x |  |  |  | x
US-003692 | Yes | mchin@servicesource.com | Jolene Chin | Mei Yin | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | mforcades@servicesource.com | Forcades | Melodie | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | mabdulmanak@servicesource.com | Abdul Manak | Mohamad Tarmizi | Active | Operations Manager | SSI Zenith Operations Services | Sales Ops Users |  |  | x |  |  |  | x | [6 empty] | x | x |  |  |  |  | x
US-003692 | Yes | maziz@servicesource.com | Aziz | Muhammad Hazwan Bin | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | nhamdan@servicesource.com | Hamdan | Nashmin | Active | Operations Rep | SSI Zenith Operations Services | APJ Ops Users |  |  | x |  |  |  | x | [6 empty] | x | [6 empty] | x
US-003692 | Yes | nmarcassoli@servicesource.com | Marcassoli | Noemi | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | pheapes@servicesource.com | Heapes | Philip | Active | Sales Manager | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x |  |  |  |  | x |  |  |  | x
US-003692 | Yes | pvasamsetti@servicesource.com | Vasamsetti | Prasad | Active | Data Services | Read Only | Sales Ops Users |  |  | x
US-003692 | Yes | kschweinberg@servicesource.com | Schweinberg | Kenneth | Active | Sales Operations Analyst | SSI Zenith Read Only | Sales Ops Users |  |  | x | [15 empty] | x |  |  | x
US-003692 | Yes | rmieda@servicesource.com | Mieda | Reika | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | rtakizawa@servicesource.com | Takizawa | Rieko | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | rtiang@servicesource.com | Tiang | Roxanne | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | rnichting@servicesource.com | Nichting | Ryan | Active | Sales Manager | SSI Zenith Read Only | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x |  |  |  |  | x |  |  |  | x
US-003692 | Yes | smuller@servicesource.com | Muller | Sara | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | ssyedsalleh@servicesource.com | Syed Salleh | Sharifah Mariam | Active | Operations Rep | SSI Zenith Operations Services | APJ Ops Users |  |  | x |  |  |  | x | [6 empty] | x | [6 empty] | x
US-003692 | Yes | sulim@servicesource.com | Lim | Su | Active | Sales Rep | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | sstach@servicesource.com | Smaga | Sylwia | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | toconnor@servicesource.com | O'Connor | Trevor | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | vagrawal@servicesource.com | Agrawal | Vigyan | Active | Data Services | Read Only | Sales Ops Users |  |  | x
US-003692 | Yes | vhahn@servicesource.com | Hahn | Vivien | Active | Sales Rep | SSI Zenith Sales | EMEA Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | ytay@servicesource.com | Tay | Melanie | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | ytachibana@servicesource.com | Tachibana | Yuriko | Active | Sales Rep | SSI Zenith Sales | APJ Sales Users |  |  | x |  |  |  | x | [6 empty] | x | [9 empty] | x
US-003692 | Yes | kborkenhagen@servicesource.com | Borkenhagen | Keiko | Active | Sales Manager | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | X |  | X |  |  |  |  | X |  |  |  | X | X | X |  |  | X
US-003692 | Yes | lthomas@servicesource.com | Thomas | Lori | Active | Sales Manager | SSI Zenith Sales | NALA Sales Users |  |  | x |  |  |  | X |  | X |  |  |  |  | X |  |  |  | X | X | X |  |  | X
US-003692 | Yes | dperson@servicesource.com | Person | David | Active |  | Admin
US-003692 | Yes | cireland@servicesource.com | Ireland | Colin | Inactive
US-003692 | Yes | afragale@servicesource.com | Fragale | Anna | Inactive
US-003692 | Yes | akumar@servicesource.com | Kumar | Arun | Inactive
US-003692 | Yes | awainwright@servicesource.com | Wainwright | Ashton | Inactive
US-003692 | Yes | blee@servicesource.com | Lee | Benedict Kah Hock | Inactive
US-003692 | Yes | bnono@servicesource.com | Nono | Bertin | Inactive
US-003692 | Yes | bcosta@servicesource.com | Costa | Blanche | Inactive
US-003692 | Yes | bang@servicesource.com | Ang | Boon Wee | Inactive
US-003692 | Yes | bfudge@servicesource.com | Fudge | Brenda | Inactive
US-003692 | Yes | bmcaleese@servicesource.com | McAleese-Jergins | Bryan | Inactive
US-003692 | Yes | bholbecq@servicesource.com | Holbecq | Bryce | Inactive
US-003692 | Yes | cjjones@servicesource.com | Jones | Chad | Inactive
US-003692 | Yes | cleong@servicesource.com | Leong | Christina | Inactive
US-003692 | Yes | dchaniott@servicesource.com | Chaniott | Daniel | Inactive
US-003692 | Yes | dahmed@servicesource.com | Ahmed | David | Inactive
US-003692 | Yes | dwilcox@servicesource.com | Wilcox | William | Inactive
US-003692 | Yes | kloh@servicesource.com | Loh | Derek | Inactive
US-003692 | Yes | dgcoelho@servicesource.com | Coelho | Diana | Inactive
US-003692 | Yes | eeisenberg@servicesource.com | Eisenberg | Eli | Inactive
US-003692 | Yes | ethomasson@servicesource.com | Thomasson | Ethan | Inactive
US-003692 | Yes | hbintehassan@servicesource.com | Binte Hassan | Hartini | Inactive
US-003692 | Yes | jfazio@servicesource.com | Fazio | Jared | Inactive
US-003692 | Yes | jchoong@servicesource.com | Yan Choong | Jia | Inactive
US-003692 | Yes | jong@servicesource.com | Ong | Jingwen | Inactive
US-003692 | Yes | jarpas@servicesource.com | Arpas | Joanna | Inactive
US-003692 | Yes | jtin@servicesource.com | Tin | Jonathan | Inactive
US-003692 | Yes | jmaroto@servicesource.com | Maroto | Jose | Inactive
US-003692 | Yes | jhomer@servicesource.com | Homer | Josh | Inactive
US-003692 | Yes | jonelson@servicesource.com | Nelson | Joshua | Inactive
US-003692 | Yes | jbrown@servicesource.com | Brown | Justin | Inactive
US-003692 | Yes | kfialho@servicesource.com | Fialho | Keith | Inactive
US-003692 | Yes | lgrant@servicesource.com | Grant | Laura | Inactive
US-003692 | Yes | ltromben@servicesource.com | Tromben | Laura | Inactive
US-003692 | Yes | mstevens@servicesource.com | Stevens | Matt | Inactive
US-003692 | Yes | mtay@servicesource.com | Tay | Monique | Inactive
US-003692 | Yes | oconnolly@servicesource.com | Connolly | Oisin | Inactive
US-003692 | Yes | pandrzejewski@servicesource.com | Andrzejewski | Pawel | Inactive
US-003692 | Yes | rrowden@servicesource.com | Rowden | Rebecca | Inactive
US-003692 | Yes | riscott@servicesource.com | Scott | Richard | Inactive
US-003692 | Yes | sdeshpande@servicesource.com | Deshpande | Salil | Inactive
US-003692 | Yes | scarter@servicesource.com | Carter | Sara | Inactive
US-003692 | Yes | svincent@servicesource.com | Vincent | Sarah | Inactive
US-003692 | Yes | sengel@servicesource.com | Engal | Saskia | Inactive
US-003692 | Yes | scaro@servicesource.com | Caro | Sequina | Inactive
US-003692 | Yes | slow@servicesource.com | Low | Shau Wei | Inactive
US-003692 | Yes | shng@servicesource.com | Ng | Giselle | Inactive
US-003692 | Yes | siismail@servicesource.com | Sandora | Siti | Inactive
US-003692 | Yes | tdodd@servicesource.com | Dodd | Tera | Inactive
US-003692 | Yes | tsikes@servicesource.com | Sikes | Troy | Inactive
US-003692 | Yes | vmartin@servicesource.com | Martin | Violeta | Inactive
US-003692 | Yes | wbaran@servicesource.com | Baran | Wieslawa | Inactive
US-003692 | Yes | ykobayakawa@servicesource.com | Kobayakawa | Yoji | Inactive
US-003692 | Yes | ykumamaru@servicesource.com | Kumamaru | Yu | Inactive
US-003692 | Yes | yholmes@servicesource.com | Holmes | Yvonne | Inactive
US-003692 | Yes | zabdulrahman@servicesource.com | Abdul Rahman | Zarie | Inactive

## Opportunities
Use Cases # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003694 | Add Google SFDC ID, Original Order Number & Direct/Channel to page layout |  | All Users | Navigate to "Opportunities" tab |  | Opportunities tab load |  | Passed |  |  | Passed | 9
US-003694 |  |  |  | Click on "New" button |  | Select Opportunity Record Type page |  | Passed |  |  | Failed | 2
US-003694 |  |  |  | Select "Opportunity - Edit" then click "Continue" button |  | New Opportunity Edit page load | [6 empty] | Passed
US-003694 |  |  |  | Verify for additional Partner fields |  | The following fields should be visible: Direct/Channel (Under Partner Information) Google SFDC ID (Under Opportunity Detail) Original Order Number (under Order Information) |  | Failed | 233321 |  |  |  | Failed
US-003694 |  |  |  | Verify new fields permission |  | Direct/Channel (picklist) Google SFDC ID (Text) Original Order Number (Text) - editable for all except SalesOps |  | Failed | 233321 |  |  |  | Not Tested
US-003695 | Add Picklist for Client Region, Client Theatre, Currency, Engagement type and Client Territory |  | All Users | Verify "Business Line" picklist |  | The following values: Core - removed Maps - Added |  | Passed
US-003695 |  |  |  | Verify "Client Territory" picklist |  | The following values: USA - removed TBD - Added |  | Passed
US-003695 |  |  |  | Verify "Renewal Currencies" picklist |  | The following values: AUD, CHF, CYN, NZD, SGD, ZAR - Removed JPY - Added |  | Passed
US-003695 |  |  |  | Verify "SSI Theatre" picklist |  | The following values: APJ - Removed APAC - Added |  | Passed
US-003695 |  |  |  | Verify "Client Regions" picklist |  | The following values: USA - Removed ANZ, ASIA, Canada, Commercial, EMEA, EMEA - DACH, EMEA - FRITES, EMEA - Other, EMEA - UK, Federal, Japan, LATAM, MIDDLE EAST - UNITED ARAB EMIRATES, NA, Other APAC, SLED, UK&I - UNITED KINGDOM - Added |  | Passed
US-003696 | Update Opportunity Product |  |  | Navigate to "Opportunities" tab |  | Opportunities tab load |  | Passed
US-003696 |  |  |  | Click on any existing Opportunity with Product Line Item & Renewable Line Item |  | Opportunities details page load |  | Passed |  | Can't create Product Line Item as SalesMgr or OpsMgr
US-003696 |  |  |  | Click on "Edit" for any existing Opportunity Product Line Item |  | Opportunity Product Details page load |  | Not Tested
US-003696 |  |  |  | Verify updated fields |  | The following fields should be visible: Covered Product - Text field Product - Text field |  | Not Tested
US-003696 |  |  |  | Verify updated fields permission |  | The following fields should be editable for all users except SalesOps: Covered Product Product |  | Not Tested
US-003697 | Update to Renewable Line Item |  |  | Click on "Opportunity Name" link |  | Opportunities details page load |  | Not Tested
US-003697 |  |  |  | Click on "Edit" for any existing Renewable Line Item |  | Renewable Line Item page load |  | Not Tested | 233334
US-003697 |  |  |  | Verify new and updated fields |  | The following fields should be visible: Existing Product - Text field Covered Product - Text field |  | Not Tested
US-003697 |  |  |  | Verify new updated fields permission |  | Under Additional Information, the following fields should be editable for all users except SalesOps: Existing Product Covered Product |  | Not Tested
US-003690 | Disabled Rule: SSI_ZTH__Stage_Closed_Sale |  |  | Navigate to "Opportunities" tab |  | Opportunities tab load
US-003690 |  |  |  | Click on any existing Opportunity with Renewable Line Item & Quote |  | Opportunities details page load
US-003690 |  |  |  | Double click on "Stage" field, update value to "Closed Sale" then click "OK" |  | Field updated
US-003690 |  |  |  | Make sure "PO Number" field is empty, then click "Save" button |  | The following message should be visible "The following fields cannot be blank: PO Number"

## Cases
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003693 | Case Types by Persona |  | SalesRep, SalesMgr | Navigate to "Cases" tab |  | Opportunities tab load |  | Passed |  |  | Passed | 27
US-003693 |  |  |  | Click on "New" button |  | Select Case Record Type page load |  | Passed |  |  | Failed | 4 | Passed
US-003693 |  |  |  | Verify "Record Type" picklist |  | The following values should be visible: Booking Request Data Processing Request Data Update Request Lead Submission Request Quote Request Reporting Request |  | Passed |  |  |  |  | Failed
US-003693 | Submit: Lead Submission Data Update |  |  | Select "Lead Submission" then click "Continue" |  | New Case Edit page load *Case Record Type should shows "Lead Submission" |  | Passed |  |  |  |  | Not Tested
US-003693 |  |  |  | Enter all required fields then click "Save & New" button |  | Record saved and Select Case Record Type page load |  | Passed
US-003693 |  |  |  | Select "Data Update" then click "Continue" |  | New Case Edit page load *Case Record Type should shows "Data Update" |  | Passed
US-003693 |  |  |  | Enter all required fields |  | Fields updated |  | Passed
US-003693 |  |  |  | Select "Priority = High" then click "Save " button |  | Record saved |  | Passed
US-003687 | Changed Custom to 'Yes' for all SLA's |  |  | Verify Case Milestone and Target Date |  | The following should shows: Case Milestone = 720 mins (12 hours) Entitlement Process Start Time - Target Date = 12hrs (Business Hrs) |  | Failed | 233317
US-003693 |  |  | OpsRep, OpsMgr | Navigate to "Cases" tab |  | Opportunities tab load |  | Passed
US-003693 |  |  |  | Click on "New" button |  | Select Case Record Type page load |  | Passed
US-003693 |  |  |  | Verify "Record Type" picklist |  | The following values should be visible: Booking Request Data Processing Request Data Update Request Quote Request Reporting Request |  | Passed
US-003693 | Submit: Quote Data Processing |  |  | Select "Quote" then click "Continue" |  | New Case Edit page load *Case Record Type should shows "Quote" |  | Passed
US-003693 |  |  |  | Enter all required fields |  | Fields updated |  | Passed
US-003693 |  |  |  | Select "Priority = Normal" then click "Save " button |  | Record saved |  | Passed
US-003687 | Changed Custom to 'Yes' for all SLA's |  |  | Verify Case Milestone and Target Date |  | The following should shows: Case Milestone = 1440 mins (24 hours) Entitlement Process Start Time - Target Date = 24hrs (Business Hrs) |  | Failed | 233317
US-003693 |  |  | SalesOps | Navigate to "Cases" tab |  | Opportunities tab load |  | Passed
US-003693 |  |  |  | Click on "New" button |  | Select Case Record Type page load |  | Passed
US-003693 |  |  |  | Verify "Record Type" picklist |  | The following values should be visible: Booking Request Data Update Request Reporting Request |  | Passed
US-003693 | Submit: Booking Report |  |  | Select "Booking" then click "Continue" |  | New Case Edit page load *Case Record Type should shows "Booking Request" |  | Passed
US-003693 |  |  |  | Enter all required fields |  | Fields updated |  | Passed
US-003693 |  |  |  | Select "Priority = Low" then click "Save " button |  | Record saved |  | Passed
US-003687 | Changed Custom to 'Yes' for all SLA's |  |  | Verify Case Milestone and Target Date |  | The following should shows: Case Milestone = 2880 mins (48 hours) Entitlement Process Start Time - Target Date = 48hrs (Business Hrs) |  | Failed | 233317
US-003687 |  |  |  | Double click on "Request Escalation" then check the checkbox |  | "Request Escalation" checked |  | Passed
US-003687 |  |  |  | Double click on "Escalation Reason" enter some text then click "OK" |  | "Escalation Reason" updated |  | Passed
US-003687 |  |  |  | Click on "Save" button |  | Case Details page reload and there should be a lock icon next to "Edit" button |  | Passed
US-003687 |  |  |  | Logout then log back in as either OpsMgr/SalesMgr |  | Login successfully |  | Passed
US-003687 |  |  |  | Click "Approve/Reject" link for the specific Case# in the "Items to Approve" section on Home tab |  | Approve/Reject Approval Request page load |  | Passed
US-003687 |  |  |  | Click "Approve" button |  | Case Details page load |  | Passed
US-003687 |  |  |  | Review "Priority" and "Escalated" value. |  | The following should be visible: Priority = Low Escalated = checked |  | Passed
US-003687 |  |  |  | Scroll to "Case Management" and review "Target Date" & Case Milestone |  | Case Milestone should show "NALA Escalation" Entitlement Process Start Time - Target Date = 12 hours (Business Hrs) |  | Failed | 233317
US-003689 | Disable No Service Approval process. |  | All Users | Navigate to "Cases" tab |  | Cases tab load
US-003689 |  |  |  | Click on "New" button |  | New Case Edit page load
US-003689 |  |  |  | Enter all required fields and set "Sub Case Type = No Service" "SSI Result Reason = any NS value" |  | All fields updated correctly
US-003689 |  |  |  | Click "Save" |  | New case saved successfully and there should be NO lock icon next to edit button
US-003689 |  |  |  | Navigate to "Cases" tab |  | Cases tab load
US-003689 |  |  |  | Click on "New" button |  | New Case Edit page load
US-003689 |  |  |  | Enter all required fields and set "Sub Case Type = House Account" "SSI Result Reason = any HA value" |  | All fields updated correctly
US-003689 |  |  |  | Click "Save" |  | New case saved successfully and there should be a lock icon next to edit button
US-003689 |  |  |  | Scroll down to "Approval History" section |  | Overall Status should be showing "Pending" and Assigned to should be "Sales & Ops Manager Queue"
US-003689 |  |  | SalesMgr, OpsMgr | Login as SalesMgr/OpsMgr |  | Home tab load
US-003689 |  |  |  | Lookup and click on the above case |  | Case Details page load
US-003689 |  |  |  | Scroll down to "Approval History" |  | Reassign/Approve/Reject link should be visible
US-003689 |  |  |  | Click on "Approval/Reject" link |  | Approve/Reject Approval Request page load
US-003689 |  |  |  | Enter some comments then click "Approve" |  | Case Details page load lock should be removed and the following should shows: HA/ NS meets approval criteria: Checked HA/NS Approval Status: HA - Approved

## Tasks
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003698 | Task Types by Persona |  | All Users | Navigate to "Home" tab |  | Home tab load |  |  |  |  | Passed | 0
US-003698 |  |  |  | Click "New" button for My Tasks |  | Select Task Record Type page load |  |  |  |  | Failed | 0
US-003698 |  |  |  | Verify Task Type picklist |  | The following should be visible: Standard Email Phone | [6 empty] | Passed
US-003698 | Task - Email |  |  | Select " Email" from picklist then click "Continue" |  | New Task page load | [6 empty] | Failed
US-003698 |  |  |  | Enter all required fields |  | fields updated | [6 empty] | Not Tested
US-003698 |  |  |  | Click "Save & New Task" button |  | Task saved and "Select Task Record Type" page load
US-003698 | Task - Phone Calls |  |  | Select "Phone Calls" from picklist then click "Continue" |  | New Task page load
US-003698 |  |  |  | Enter all required fields |  | fields updated
US-003698 |  |  |  | Click "Save & New Task" button |  | Task saved and "Select Task Record Type" page load
US-003698 | Task - Standard |  |  | Select "Standard" from picklist then click "Continue" |  | New Task page load
US-003698 |  |  |  | Enter all required fields |  | fields updated
US-003698 |  |  |  | Click "Save" button |  | Task saved successfully

## Leads (hidden)
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
[11 empty] | Passed | 0
[11 empty] | Failed | 0
Passed
Failed
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Failed
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested

## Users12
Update |  | User Register (Add lines for deployed Users)
User Story | Custom | Username | LastName | FirstName | User Status | Persona | Profile | Public Group | GridBuddy | Data.com | Channel | Channel Community | Channel Community | Channel NetOps | CLM Quote Extension | CSM | CSM NetOps | Entitlements Extension | Lookup Rollup Summaries - Configure Rollups | Lookup Rollup Summaries - Process Rollups | NonCSM | Renew | Renew NetOps | SSI Zenith Admin Permission | SSI Zenith Data Services Permission | SSI Zenith Manage Public List View Permission | SSI Zenith Manage Report & Dashboard Permission | SSI Zenith Operation Services Manager Permission | SSI Zenith Operation Services Rep Permission | SSI Zenith Read Only Permission | SSI Zenith Sales Manager Permission | SSI Zenith Sales Rep Permission | Usage Event Log Access (use only for API users)
US-003692 | Yes | CJJones@servicesource.com | Jones | Chad | Inactive
US-003692 | Yes | JHomer@servicesource.com | Homer | Josh | Inactive