## Overview
Use Case Scenario | Test Case Name | Test Script Status | Owner | # of Test Steps | Passed | Failed | Not Tested
General |  |  |  | 12 | 0 | 0 | 12
US-003809 | General configuration for Schneider | Completed | Mailene | 5
US-003810 | General calendar configuration for Schneider | Completed | Mailene | 2
US-003812 | Users who require access to Schneider's One Platform | Completed | Mailene | 3
US-003814 | Business Hours EMEA | Completed | Mailene | 2
Accounts |  |  |  | 5 | 4 | 0 | 1
US-003802 | Add new fields to the Account page layout. | Completed | Mailene | 5
Assets |  |  |  | 17 | 4 | 0 | 13
US-003803 | Add new fields to Asset page layout | Completed | Mailene | 16
US-003815 | The "Engagement Type" picklist on Assets | Completed | Mailene | 1
Contacts |  |  |  | 4 | 0 | 0 | 4
Contacts-01 | Create new contact | Completed | Mailene | 4
Location Address |  |  |  | 5 | 0 | 0 | 5
US-003805 | Remove field from Location Address page layout | Completed | Mailene | 5
Cases |  |  |  | 40 | 0 | 0 | 40
US-003811 | Case types required for all persona | Completed | Mailene | 40
Opportunities |  |  |  | 104 | 0 | 0 | 104
US-003806 | Add new fields to the Opportunity page layout. | Completed | Mailene | 70
Opportunities Products |  |  |  | 16 | 0 | 0 | 16
US-003807 | Add new fields to the Opportunity page layout. | Completed | Mailene | 16
US-003808 | Renewable Line Item | Incomplete | Mailene | 2
Quotes |  |  |  | 0 | 5 | 0 | -5
Quotes-01 | Create new Quotes | Completed | Mailene | 0
Tasks |  |  |  | 12 | 0 | 0 | 12
Tasks-01 | Create new Tasks | Completed | Mailene | 12
Leads |  |  |  | 5 | 2 | 0 | 3
US-003804 | Add new fields to Leads page layout | Completed | Mailene | 5
Total |  |  |  | 220 | 15 | 0 | 205

## General
Use Cases # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003809 | General configuration for Schneider | Configuration | Admin | Login as Admin user |  | Home tab load |  |  |  |  | Passed | 0
US-003809 |  | Configuration |  | Click on "Setup" |  | Force.com home load |  |  |  |  | Failed | 0 | Passed
US-003809 |  | Configuration |  | Click on "Company Profile" |  | Company Profile menu expand | [6 empty] | Failed
US-003809 |  | Configuration |  | Click on "Manage Currencies" |  | Currency page load | [6 empty] | Not Tested
US-003809 |  | Configuration |  | Verify currency setting |  | 1. User should see "GBP" as based currency. 2. EUR is listed as the other currency with the exchange rate of "1.18"
US-003812 |  | Configuration |  | Click on "Manage User" arrow |  | Manage User menu expand
US-003812 |  | Configuration |  | Click on "Users" |  | All Users page load
US-003812 |  | Configuration |  | Verify users profile |  | User Profiles should match "Users" tab in config. guide
US-003810 | General calendar configuration for Schneider | Configuration |  | Click on "Company Profile" |  | Company Profile menu expand
US-003810 |  | Configuration |  | Click on "Fiscal Year" |  | Fiscal calendar should shows: - Jan-Mar Q1 - Apr-Jun Q2 - Jul-Sep Q3 - Oct-Dec Q4
US-003814 | Business Hours EMEA | Configuration |  | Click on "Business Hours" |  | Organization Business Hours page load
US-003814 |  | Configuration |  | Click on "EMEA" |  | The following should be visible: Sunday: No Hours Monday: 8:00 AM to 5:00 PM Tuesday: 8:00 AM to 5:00 PM Wednesday: 8:00 AM to 5:00 PM Thursday: 8:00 AM to 5:00 PM Friday: 8:00 AM to 5:00 PM Saturday No Hours
Passed
Failed
Note on A44: Mailene Mac: Need to add scripts for Batch Jobs

## Accounts
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003802 | Add new fields to the Account page layout. | Configuration | All Users | Click on "Accounts" tab |  | Accounts tab load |  | Passed |  |  | Passed | 4
US-003802 |  | Configuration |  | Click on "New" |  | New Account Edit page load |  | Passed |  |  | Failed | 0 | Passed
US-003802 |  | Configuration |  | Verify new field |  | Field "Account Zip Code" should be visible below Account Location |  | Passed |  |  |  |  | Failed
US-003802 |  | Configuration |  | Verify "Account Zip Code" field type and permission |  | Field "Account Zip Code" should be a text field and editable for all users profile except SalesOps |  | Passed |  |  |  |  | Not Tested
US-003802 | Update Type picklist | Configuration |  | Verify "Type" picklist values |  | The following values should be visible: PROXIMITY Disti Partner

## Assets
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003803 | Add new fields to Asset page layout | Configuration | All Users | Click on "Assets" tab |  | Assets tab load |  | Passed |  |  | Passed | 4
US-003803 |  | Configuration |  | Click on "New" |  | New Contact Edit page load |  | Passed |  |  | Failed | 0 | Passed
US-003803 |  | Configuration |  | Verify new field "Territory" |  | Field "Territory" should be visible under Contact field in the Asset Details section |  | Passed |  |  |  |  | Failed
US-003803 |  | Configuration |  | Verify "Territory" field type and permission |  | Field "Territory" should be a text field Read Only - SalesRep, SalesMgr Editable - OpsRep, OpsMgr |  | Passed |  |  |  |  | Not Tested
US-003803 |  | Configuration |  | Verify new field "EOPL" |  | Field "EOPL" should be visible under Territory field in the Asset Details section
US-003803 |  | Configuration |  | Verify "EOPL" field type and permission |  | Field "EOPL" should be a date field Read Only - SalesRep, SalesMgr Editable - OpsRep, OpsMgr
US-003803 |  | Configuration |  | Verify new field "EOSL" |  | Field "EOSL" should be visible under EOPL field in the Asset Details section
US-003803 |  | Configuration |  | Verify "EOSL" field type and permission |  | Field "EOSL" should be a date field Read Only - SalesRep, SalesMgr Editable - OpsRep, OpsMgr
US-003803 |  | Configuration |  | Verify new field "Engagement Type" |  | Field "Engagement Type" should be visible under Covered Asset field in the Asset Details section
US-003803 |  | Configuration |  | Verify "Engagement Type" field type and permission |  | Field "Engagement Type" should be a picklist Read Only - SalesRep, SalesMgr Editable - OpsRep, OpsMgr
US-003815 | US-003815 | Configuration |  | Verify "Engagement Type" picklist values |  | The following values should be visible: SREV Client
US-003803 |  | Configuration |  | Verify new field "Service Sales Owner" |  | Field "Service Sales Owner" should be visible under Engagement Type field in the Asset Details section
US-003803 |  | Configuration |  | Verify "Service Sales Owner" field type and permission |  | Field "Service Sales Owner" should be a Lookup of Users Read Only - SalesRep, SalesMgr Editable - OpsRep, OpsMgr
US-003803 |  | Configuration |  | Verify new field "Warranty End Date" |  | Field "Warranty End Date" should be visible under Install Date field in the Asset Details section
US-003803 |  | Configuration |  | Verify "Warranty End Date" field type and permission |  | Field "Warranty End Date" should be a date field Read Only - SalesRep, SalesMgr Editable - OpsRep, OpsMgr
US-003803 |  | Configuration |  | Enter all required fields |  | Fields updated
US-003803 |  | Configuration |  | Click "Save" |  | Asset created successfully.

## Contacts
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
Contacts-01 | Create new contact | Configuration | All Users | Click on "Contacts" tab |  | Contacts tab load |  | Passed |  |  | Passed | 4
Contacts-01 |  | Configuration |  | Click on "New" |  | Contacts Edit page load |  | Passed |  |  | Failed | 0 | Passed
Contacts-01 |  | Configuration |  | Enter a value for all required fields |  | Fields updated |  | Passed |  |  |  |  | Failed
Contacts-01 |  | Configuration |  | Click "Save" |  | Contact created successfully |  | Passed |  |  |  |  | Not Tested

## Location Address
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003805 | Remove field from Location Address page layout | Configuration | All Users | Click on "Location Address" tab |  | Location Address tab load |  |  |  |  | Passed | 0
US-003805 |  | Configuration |  | Click on "New" |  | Location Address Edit page load |  |  |  |  | Failed | 0 | Passed
US-003805 |  | Configuration |  | Verify removal of field |  | "State or Province" field should not be visible | [6 empty] | Failed
US-003805 |  | Configuration |  | Enter a value for all required fields |  | Fields updated | [6 empty] | Not Tested
US-003805 |  |  |  | Click "Save" |  | Contact created successfully

## Cases
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003811 | Case types required for all persona | Configuration | All Users | Click on "Cases" tab |  | Cases tab load |  |  |  |  | Passed | 0
US-003811 |  | Configuration |  | Click on "New" |  | Select Case Record Type page load |  |  |  |  | Failed | 0 | Passed
US-003811 | Booking Request | Configuration |  | Select "Booking Request" from the picklist |  | Record Type selected | [6 empty] | Failed
US-003811 |  | Configuration |  | Click "Continue" |  | New Case Edit page load | [6 empty] | Not Tested
US-003811 |  | Configuration |  | Enter all required fields |  | Fields updated
US-003811 |  | Configuration |  | Click "Save & New" |  | Case created and Select Case Record Type page load
US-003811 | Lead Submission | Configuration |  | Select "Lead Submission" from the picklist |  | Record Type selected
US-003811 |  | Configuration |  | Click "Continue" |  | New Case Edit page load
US-003811 |  | Configuration |  | Enter all required fields |  | Fields updated
US-003811 |  | Configuration |  | Click "Save & New" |  | Case created and Select Case Record Type page load
US-003811 | Quote Request | Configuration |  | Select "Quote Request" from the picklist |  | Record Type selected
US-003811 |  | Configuration |  | Click "Continue" |  | New Case Edit page load
US-003811 |  | Configuration |  | Enter all required fields |  | Fields updated
US-003811 |  | Configuration |  | Click "Save & New" |  | Case created and Select Case Record Type page load
US-003811 | Reporting Request | Configuration |  | Select "Reporting Request" from the picklist |  | Record Type selected
US-003811 |  | Configuration |  | Click "Continue" |  | New Case Edit page load
US-003811 |  | Configuration |  | Enter all required fields |  | Fields updated
US-003811 |  | Configuration |  | Click "Save & New" |  | Case created and Select Case Record Type page load
US-003811 | Data Update Request | Configuration | OpsRep, OpsMgr | Select "Data Update Request" from the picklist |  | Record Type selected
US-003811 |  | Configuration |  | Click "Continue" |  | New Case Edit page load
US-003811 |  | Configuration |  | Enter all required fields |  | Fields updated
US-003811 |  | Configuration |  | Click "Save" |  | Case created successfully
US-003811 |  | Configuration |  | Update case "Priority=Low" then click "Save" |  | Case updated successfully
US-003811 |  | Configuration |  | Verify Case Milestones |  | Case Milestones should be showing "NALA 48hrs"
US-003811 |  | Configuration |  | Verify Case Target Date |  | Target Date should be 48 hrs CALCULATION Entitlement Process Start Time - Target Date = 48 hours (Business Hrs)
US-003811 |  | Configuration |  | Update case "Priority=Normal" then click "Save" |  | Case updated successfully
US-003811 |  | Configuration |  | Verify Case Milestones |  | Case Milestones should be showing "NALA 24hrs"
US-003811 |  | Configuration |  | Verify Case Target Date |  | Target Date should be 24 hrs CALCULATION Entitlement Process Start Time - Target Date =24 hours (Business Hrs)
US-003811 |  | Configuration |  | Update case "Priority=High" then click "Save" |  | Case updated successfully
US-003811 |  | Configuration |  | Verify Case Milestones |  | Case Milestones should be showing "NALA 24hrs"
US-003811 |  | Configuration |  | Verify Case Target Date |  | Target Date should be 12 hrs CALCULATION Entitlement Process Start Time - Target Date =12 hours (Business Hrs)
US-003811 |  | Configuration |  | Update "Case Sub Type = HA/HS" |  | Field updated
US-003811 |  | Configuration |  | Update "Renewal Status" to any existing value then click "OK" |  | Field updated
US-003811 |  | Configuration |  | Click "Save" |  | Case updated successfully and there should be a Lock icon next to "Edit" button.
US-003811 |  | Configuration |  | Verify Approval process |  | Case Owner should shows "Sales and Ops Manager Queue". *Note the case#
US-003811 |  | Configuration | OpsMgr, SalesMgr | Login as OpsMgr/SalesMgr |  | Home tab load
US-003811 |  | Configuration |  | From Items to Approve section, click on the case# |  | Case Details page load
US-003811 |  | Configuration |  | From Approval History section, click on Approved/Reject Link |  | Approve/Reject Approval Request page load
US-003811 |  | Configuration |  | Enter some text into comments then click "Approve" button |  | Case page load
US-003811 |  | Configuration |  | Verify case approved |  | Lock icon should no longer be visible and "HA/ NS meets approval criteria" checkbox should be checked.

## Opportunities
Use Cases # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003806 | Add new fields to the Opportunity page layout. | Configuration | SalesRep, SalesMgr, OpsRep, OpsMgr | Click on "Opportunities" tab |  | Opportunities tab load |  |  |  |  | Passed | 0
US-003806 |  | Configuration |  | Click on "New" |  | Select Opportunity Record Type page load |  |  |  |  | Failed | 0
US-003806 |  | Configuration |  | Select "Opportunity - Edit" then click "Continue" |  | New Opportunity Edit page load
US-003806 |  | Configuration |  | Verify "Business Line" picklist value |  | The following values should be visible: Energy ITB
US-003806 |  | Configuration |  | Verify "Client Sales Stage" picklist value |  | The following values should be visible: 1 - Understand Business Process 3 - Qualify Opportunity 4 - Influence & Develop 5 - Prepare & Bid 6 - Negotiate & Win 7 - Won
US-003806 |  | Configuration |  | Verify "Client Territory" picklist value |  | The following values should be visible: EMEA
US-003806 |  | Configuration |  | Verify new field "Boop Converted Value" |  | Field "Boop Converted Value" should be visible under Boop Reporting section | [6 empty] | Passed
US-003806 |  | Configuration |  | Verify "Boop Converted Value" field type and permission |  | Field "Boop Converted Value" should be a currency field Read Only - all user profile | [6 empty] | Failed
US-003806 |  | Configuration |  | Verify new field "Boop Created Date" |  | Field "Boop Created Date" should be visible under Boop Reporting section | [6 empty] | Not Tested
US-003806 |  | Configuration |  | Verify "Boop Created Date" field type and permission |  | Field "Boop Created Date" should be a date field Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "Boop Status" |  | Field "Boop Status" should be visible under Boop Reporting section | [6 empty] | Not Tested
US-003806 |  | Configuration |  | Verify "Boop Status" field type and permission |  | Field "Boop Status" should be a picklist. Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "First Quote Delivered Date " |  | Field "First Quote Delivered Date" should be visible under Renewals Indicators section
US-003806 |  | Configuration |  | Verify "First Quote Delivered Date " field type and permission |  | Field "First Quote Delivered Date" should be a date/time field Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "Insight Reason" |  | Field "Insight Reason" should be visible under Opportunity Details section
US-003806 |  | Configuration |  | Verify "Insight Reason " field type and permission |  | Field "Insight Reason" should be a picklist editable for all user profile except SalesOps
US-003806 |  | Configuration |  | Verify new field "Agreement Number " |  | Field "Agreement Number " should be visible under Opportunity Details section
US-003806 |  | Configuration |  | Verify "Agreement Number" field type and permission |  | Field "Agreement Number " should be a text field Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "Agreement Name " |  | Field "Agreement Name " should be visible under Opportunity Details section
US-003806 |  | Configuration |  | Verify "Agreement Name" field type and permission |  | Field "Agreement Name " should be a text field Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "Existing PO Number" |  | Field "Existing PO Number" should be visible under Opportunity Details section
US-003806 |  | Configuration |  | Verify "Existing PO Number" field type and permission |  | Field "Existing PO Number" should be a text field Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "New Contract Number" |  | Field "New Contract Number" should be visible under Order Information section
US-003806 |  | Configuration |  | Verify "New Contract Number" field type and permission |  | Field "New Contract Number" should be a text field, editable for all user profile except SalesOps
US-003806 |  | Configuration |  | Verify new field "Forecasting Status" |  | Field "Forecasting Status" should be visible under Renewal Indicators section
US-003806 |  | Configuration |  | Verify "Forecasting Status" field type and permission |  | Field "Forecasting Status" should be a text formula field Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "Quoting Status" |  | Field "Quoting Status" should be visible under Renewal Indicators section
US-003806 |  | Configuration |  | Verify "Quoting Status" field type and permission |  | Field "Quoting Status" should be a text formula field Read Only - all user profile
US-003806 |  | Configuration |  | Verify new field "Contacted Status" |  | Field "Contacted Status" should be visible under Renewal Indicators section
US-003806 |  | Configuration |  | Verify "Contacted Status" field type and permission |  | Field "Contacted Status" should be a text formula field Read Only - all user profile
US-003806 |  | Configuration |  | Enter all required fields |  | Fields updated
US-003806 |  | Configuration |  | Click "Save" |  | Opportunity created successfully
US-003806 |  | Configuration |  | Verify "Boop Converted Value" |  | This should be the Opportunity Total Amount converted to EUR.
US-003806 |  | Configuration |  | Verify "Boop Created Date" |  | If All RLI "ODS value is blank: Boop Created date = First contact date should be pulled in here. If first contact date is blank: Book Created date = opportunity created date |  |  |  | Need to verify the logic of this date with Dave B.
US-003806 |  | Configuration |  | Update Opportunity Stage = Not Contacted. Verify "Insight Reason" picklist. |  | The following values should be visible: Awaiting NS/HA Confirmed Correct Contact Contact Not Found Contact Obtained Incorrect Contact Install Base Report Created On Hold - By Client Support Required Unresponsive
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Not Quoted Contacted Status = Not Contacted Forecasting Status = Not Contacted
US-003806 |  | Configuration |  | Update Opportunity Stage = Attempted Verrify "Insight Reason" picklist. |  | The following values should be visible: Support Required Unresponsive
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Not Quoted Contacted Status = Not Contacted Forecasting Status = Not Contacted
US-003806 |  | Configuration |  | Update Opportunity Stage = Contacted Verrify "Insight Reason" picklist. |  | The following values should be visible: Awaiting NS/HA Confirmed Correct Contact Incorrect Contact Install Base Report Created Install Base Report Sent On Hold - By Client Potential Loss Risk Reseller / Distributor Risk Due To Budget Self Maintain Risk Support Required Third Party Risk Under Review By Customer Unresponsive Value Under Question
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Not Quoted Contacted Status = Contacted Forecasting Status = Contacted
US-003806 |  | Configuration |  | Update Opportunity Stage = Quote Request Verrify "Insight Reason" picklist. |  | The following values should be visible: Support Required
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Not Quoted Contacted Status = Contacted Forecasting Status = Quoted
US-003806 |  | Configuration |  | Update Opportunity Stage = Quote Completed Verrify "Insight Reason" picklist. |  | The following values should be visible: Support Required
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Quoted Contacted Status = Contacted Forecasting Status = Quoted
US-003806 |  | Configuration |  | Update Opportunity Stage = Quote Delivered Verrify "Insight Reason" picklist. |  | The following values should be visible: Awaiting NS/HA Incorrect Contact On Hold - By Client Potential Loss Risk Presently In Forecast Risk Due To Budget Self Maintain Risk Support Required Third Party Risk Under Review By Customer Unresponsive Value Under Question
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Quoted Sent Contacted Status = Contacted Forecasting Status = Quoted Sent
US-003806 |  | Configuration |  | Update Opportunity Stage = Customer Commitment Verrify "Insight Reason" picklist. |  | The following values should be visible: Support Required On Hold - By Client Presently In Forecast
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Quoted Sent Contacted Status = Contacted Forecasting Status = Committed
US-003806 |  | Configuration |  | Update Opportunity Stage = PO Received Verrify "Insight Reason" picklist. |  | The following values should be visible: Standard Multi Year Co Term Long Co Term Short Discounted
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Won Contacted Status = Won Forecasting Status = Won
US-003806 |  | Configuration |  | Verrify "Boop Status" picklist. |  | The following values should be visible: Won
US-003806 |  | Configuration |  | Update Opportunity Stage = Closed Sale Verrify "Insight Reason" picklist. |  | The following values should be visible: Standard Multi Year Co Term Long Co Term Short Discounted
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Won Contacted Status = Won Forecasting Status = Won
US-003806 |  | Configuration |  | Verrify "Boop Status" picklist. |  | The following values should be visible: Won
US-003806 |  | Configuration |  | Update Opportunity to any Stage values except for : House Account No Service PO Received Closed Sales Verrify "Boop Status" picklist. |  | The following values should be visible: Pending
US-003806 |  | Configuration |  | Update Opportunity Stage = House Account Verrify "Boop Status" picklist. |  | The following values should be visible: Cancelled
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Invalid Contacted Status = Invalid Forecasting Status = Invalid
US-003806 |  | Configuration |  | Update Opportunity Stage = No Service Verrify "Boop Status" picklist. |  | The following values should be visible: Lost
US-003806 |  | Configuration |  | Click "Save" * Some Opportunity Stage status required additional fields update in order to "Save" successfully. |  | Opportunity updated successfully
US-003806 |  | Configuration |  | Verify the following statuses: Quoting Status Contacted Status Forecasting Status |  | Verify the following statuses should be visible: Quoting Status = Lost Contacted Status = Lost Forecasting Status = Lost
US-003808 | Renewable Line Item | Configuration |  | Click on any existing "Open" Opportunity Name |  | Opportunity Details page load

## Opportunity Product
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003807 | Add new fields to the Opportunity page layout. | Configuration | SalesRep, SalesMgr, OpsRep, OpsMgr | Click on "Opportunities" tab |  | Opportunities tab load |  | Passed |  |  | Passed | 5
US-003807 |  | Configuration |  | Click on any existing Open Opportunity |  | Opportunity Details page load |  | Passed |  |  | Failed | 0 | Passed
US-003807 |  | Configuration |  | Click on "New Renewable Line Item" button |  | Renewable Line Item page |  | Passed |  |  |  |  | Failed
US-003808 | Renewable Line Item | Configuration |  | Verify "Batch Type" picklist |  | The following values should be visible: Renewals ODS Warranty IBOW Battery Expired Adds/Recovery Expired Adds/Recovery Renewal Adds/Recovery Uncovered Campaign
US-003808 |  | Configuration |  | Verify "SSI Result Reason" picklist |  | Need clarification from Dave
US-003807 |  | Configuration |  | Enter all required fields |  | Fields updated |  | Passed |  |  |  |  | Failed
US-003807 |  | Configuration |  | Click "Save" |  | Renewable Line Item created successfully |  | Passed |  |  |  |  | Not Tested
US-003807 |  | Configuration |  | Click on "Renewal Opportunity" link in the top right corner of Renewal Relationship Detail |  | Opportunity Details page load
US-003807 |  | Configuration |  | Click on "Manage Renewals" button |  | Renewal Relationship page load
US-003807 |  | Configuration |  | Select any Existing Product from the list |  | Existing Product selected
US-003807 |  | Configuration |  | Click "Rebuild Opportunity" button |  | Opportunity Details page load
US-003807 |  | Configuration |  | Click on Opportunity "Product" Edit link |  | Edit Opportunity Product details page load
US-003807 |  | Configuration |  | Verify new field "Product Name" |  | Field "Product Name" should be visible under Product Information section
US-003807 |  | Configuration |  | Verify "Product Name" field type and permission |  | Field "Product Name" should be a text field editable for all user profiles except SalesOp
US-003807 |  | Configuration |  | Verify new field "Product Line" |  | Field "Product Line" should be visible under Product Information section
US-003807 |  | Configuration |  | Verify "Product Line" field type and permission |  | Field "Product Line" should be a text field editable for all user profiles except SalesOp
US-003807 |  | Configuration |  | Add a value for the following fields Product Name Product Line |  | Fields updated
US-003807 |  | Configuration |  | Click "Save" |  | Opportunity Product updated successfully

## Quotes
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
Quotes-01 | Create new Quotes | Configuration | SalesRep, SalesMgr, OpsRep, OpsMgr | Click on "Opportunities" tab |  | Opportunities tab load |  | Passed |  |  | Passed | 5
Quotes-01 |  | Configuration |  | Click on any existing Open Opportunity |  | Opportunity Details page load |  | Passed |  |  | Failed | 0 | Passed
Quotes-01 |  | Configuration |  | Click on "New Quote" button |  | Quote Edit page load |  | Passed |  |  |  |  | Failed
Quotes-01 |  | Configuration |  | Enter all required fields |  | Fields updated |  | Passed |  |  |  |  | Not Tested
Quotes-01 |  | Configuration |  | Click "Save" |  | Contact created successfully |  | Passed |  |  |  |  | Not Tested
Quotes-01 |  | Configuration |  | Click "Add Line Item" |  | Product Selection page load
Quotes-01 |  | Configuration |  | Select any existing "Product Name" |  | Product selected
Quotes-01 |  | Configuration |  | Click "Select" button |  | Add Quote Line Items page load
Quotes-01 |  | Configuration |  | Enter all required fields |  | Fields updated
Quotes-01 |  | Configuration |  | Click "Save" |  | Quote Line Item created successfully and Quote Details page load
Quotes-01 |  | Configuration |  | Click "Start Sync" button |  | Synchronize quote and opportunity popup load
Quotes-01 |  | Configuration |  | Click "Sync" button |  | Sync Complete message load
Quotes-01 |  | Configuration |  | Click "Done" |  | Quote Details page load
Quotes-01 |  | Configuration |  | Click on "Opportunity Name" link |  | Opportunity Details page load
Quotes-01 |  |  |  | Verify Quote is sync to Opportunity |  | Syncing checkbox in the Quotes section should be checked.

## Tasks
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
Tasks-01 | Create new Tasks | Configuration | All Users | Click on "Home" tab |  | Home tab load |  |  |  |  | Passed | 0
Tasks-01 |  | Configuration |  | Click on "New" under My Tasks section |  | Select Task Record Type page load |  |  |  |  | Failed | 0
Tasks-01 | Task - Email | Configuration |  | Select "Task - Email" then click "Continue" |  | Task Edit page load | [6 empty] | Passed
Tasks-01 |  | Configuration |  | Enter all required fields then click "Save & New Task" |  | Task created successfully and Select Task Record Type page load | [6 empty] | Failed
Tasks-01 | Task - Fax | Configuration |  | Select "Task - Fax" then click "Continue" |  | Task Edit page load | [6 empty] | Not Tested
Tasks-01 |  | Configuration |  | Enter all required fields then click "Save & New Task" |  | Task created successfully and Select Task Record Type page load
Tasks-01 | Task - Inbox | Configuration |  | Select "Task - Inbox" then click "Continue" |  | Task Edit page load
Tasks-01 |  | Configuration |  | Enter all required fields then click "Save & New Task" |  | Task created successfully and Select Task Record Type page load
Tasks-01 | Task - Phone Calls | Configuration |  | Select "Task - Phone Calls" then click "Continue" |  | Task Edit page load
Tasks-01 |  | Configuration |  | Enter all required fields then click "Save & New Task" |  | Task created successfully and Select Task Record Type page load
Tasks-01 | Task - Standard | Configuration |  | Select "Task - Standard" then click "Continue" |  | Task Edit page load
Tasks-01 |  | Configuration |  | Enter all required fields then click "Save" |  | Task created successfully

## Leads
Use Case # | Test Case Name | Test Type | Role | Step Description | Data | Expected Result | Actual Result | Pass/Fail | Defect # | Comments
US-003804 | Add new fields to Leads page layout | Configuration | All Users | Click on "Leads" tab |  | Leads tab load |  | Passed |  |  | Passed | 2
US-003804 |  | Configuration |  | Click on "New" |  | Leads Edit page load |  | Passed |  |  | Failed | 0
US-003804 |  | Configuration |  | Verify "Lead Status" field picklist |  | The following values should be visible: Contacted Nurturing Qualified Unqualified On Hold | [6 empty] | Passed
US-003804 |  | Configuration |  | Enter a value for all required fields |  | Fields udpated | [6 empty] | Failed
US-003804 |  | Configuration |  | Click "Save" |  | Lead created successfully | [6 empty] | Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested
Not Tested

## User Stories Tracking (hidden)
US-003812 | Completed 12/16/2016
US-003814 | Completed 12/16/2016
US-003802 | Completed 12/16/2016
US-003803 | Completed 12/16/2016
US-003804 | Completed 12/16/2016
US-003805 | Completed 12/16/2016
US-003806 | Completed 12/16/2016
US-003807 | Completed 12/16/2016
US-003808 | Completed 12/16/2016
US-003809 | Completed 12/16/2016
US-003810 | Completed 12/16/2016
US-003811 | Completed 12/16/2016
US-003815 | Completed 12/16/2016